## Sheet1
Risk | Impact | Likelihood of Occurrence (L,M,H) | Degree of Impact (L,M,H) | Action on Trigger | Responsibility | Response Plan
Investments more than fund raised through the event | 1) Raised funds did not meet the planned amount 2) Loss incurred | M | H | Difficulty with the ticket sales | Suli | Insure the complete Event
Desired Date/Venue for the event unavailability | 1) Low audience count 2) Loss incurred | L | M | Venue not available on the desired date | Marcus | 1) No ticket sale until venue desired date is available 2) Backup venue in vicinity
Damage to facilities / safety of artists | 1) Additional repayment 2) Lower profit 3) Bad publicity for future events | H | M | 1) Equipment damage 2) Artist getting mobbed | Teresa | 3rd party security
Unforeseen weather conditions | 1) Low audience count 2) Difficulty in event management | L | L | Bad Weather Forecast two days before the event | Cathy | Make arrangements to cover the venue based on weather forecast